## Slide 1: WNC Planning Service
Progress with PAS Peer Review Actions
January – November 2023

## Slide 2: Scope of Presentation
PAS Peer Review undertaken of Planning Service in November 2022
Report of recommendations produced in early 2023 and reported to Cabinet
12 recommendations around 4 key areas:
- Vision and Leadership
- Performance Management
- Community Partnership and Engagement
- Achieving Outcomes (Local Plan, Process, and Governance)
Presentation is to detail progress to date January-November 2023 and next steps

## Slide 3: Vision and Leadership
PAS Recommendation | WNC Transformation workstream | WNC Actions
Implement the planning service restructure as quickly as possible after the new Director is in post. | Vision and Leadership | Restructure the full planning service under the ethos of ‘one service, one team’ ensuring it is fit for purpose for a unitary authority.

## Slide 4: Vision and Leadership
PAS Recommendation | WNC Transformation workstream | WNC Actions
Improve the way the planning teams are managed and led to build a stronger sense of shared purpose and start to agree and develop good: people management practices; customer focus; and behaviours and culture for the new planning service. | Vision and Leadership | Recruitment to permanent AD position. Recruitment to permanent Planning Leadership Team and Team Leader positions. External recruitment campaign launch WNC Corporate Induction for all new starters to embed our WNC culture and behaviours. Dedicated Customer Experience training for full Planning Service. Introduction of WNC line management training for Principal Planning Officers and above. Introduction of Leadership Training programme. Introduction of pilot WNC talent management and succession planning programme.

## Slide 5: Vision and Leadership
PAS Recommendation | WNC Transformation workstream | WNC Actions
Develop a workforce development plan for the service to include succession planning, training programmes for “growing your own” and introduce linked career grade role. | Vision and Leadership | Continuation of the existing career grade planner roles in the new structure. Introduction of Apprenticeships alongside the existing Graduate programme. Introduction of pilot WNC talent management and succession planning programme. Introduction of formal APC mentoring programme. Adoption of WNC corporate mentoring once pilot complete. Introduction of the Planning Service ‘Future Leaders’ programme of CPD and networking events. Continued development of the Planning Service CPD Hub.

## Slide 6: Vision and Leadership
PAS Recommendation | WNC Transformation workstream | WNC Actions
Carry out management “quick wins” including: senior manager attending team meetings to agreed frequency; introduction of regular planning service newsletters/emails; and regular one to ones for all staff prepare and implement an action plan to address staff survey results in consultation with staff. | Vision and Leadership | Introduction of a monthly full WNC Planning Service team meeting led by Assistant Director. Introduction of monthly WNC Team meetings for functional areas (Policy and Specialist Services, Development Management, Enforcement, Technical Support). Establish single WNC communication channels for the Planning Service on Outlook and Teams. Ensure a supportive culture throughout the entire Planning Service via regular 1-2-1s for all staff using the existing WNC ‘VIP’ mechanism. Adoption and ongoing implementation of the Planning Service Communications Strategy.

## Slide 7: Performance Management
PAS Recommendation | WNC Transformation workstream | WNC Actions
Analyse existing committee decisions and activity to inform a review the scheme of delegation and the number of committees to provide a committee structure and process fit for a unitary council to: improve culture and practice of planning committees to reduce the risk to the council including eliminating the use of substitute members on planning committees ensure that householder and minor applications only go to committee in exceptional circumstances trial a significantly reduced number of committees with a proportionate geographical spread (based on workload) | Performance Management | Conduct an evidence-based review and make recommendations to rationalise the number, structure and format of all WNC Planning Committees to ensure they are fit for purpose and represent a unitary council. Review and make recommendations regarding the governance and remit for the Planning Policy Committee. Provide an ongoing dedicated Member Training programme to ensure robust decision making and continuous learning alongside consistent excellent conduct.

## Slide 8: Performance Management
PAS Recommendation | WNC Transformation workstream | WNC Actions
Implement a robust service performance management framework to provide the data and information necessary to understand how the service is performing and inform what resources are needed. | Performance Management | Ensure regular meetings with DLUHC to maintain support and the sharing of best practice. Update corporate performance indicators to continually reflect statutory national targets. Embed a culture of performance management via weekly performance reports, fortnightly Planning LT and monthly Place DMT. Ensure supportive performance management throughout the entire Planning Service via regular 1-2-1s, team meetings and Appraisals. Introduce the Planning Performance Agreement Service for large schemes.

## Slide 9: Community and Partnership Engagement
PAS Recommendation | WNC Transformation workstream | WNC Actions
Consider opportunities for more planning training and development for town and parish councils, in conjunction with West Northamptonshire members and officers to include: how the planning system works; some illustrative specific planning applications with explanations around reasons for decisions; some illustrative specific enforcement cases with explanations around reasons for action or not; and some assessment of overturns and appeals showing lessons learnt. | Community and Partnership Engagement | Utilise the platform of NCALC’s existing training programme to reach Parish and Town Councils and provide bespoke training. Improve regular communication links with local councils via the Parish Briefing and a pilot Operation Focus Group. Undertake a regular satisfaction and feedback survey with the support of NCALC to inform and improve our customer experience on an ongoing basis.

## Slide 10: Community and Partnership Engagement
PAS Recommendation | WNC Transformation workstream | WNC Actions
Introduce a forum that engages with agents and customers to help shape the service and hear and address concerns. | Community and Partnership Engagement | Introduce an Agents and Developers Forum for West Northamptonshire, linking with Inward Investment and Regeneration networks as appropriate. Continue positive enabling relationships with strategic stakeholders and delivery partners, such as Homes England and key infrastructure providers. Embed a culture of customer satisfaction and continuous learning/improvement in the Planning Service for example, on ‘project closure’ ensure a customer satisfaction survey is issued and received to inform future practice and processes.

## Slide 11: Achieving Outcomes – Process Design
PAS Recommendation | WNC Transformation workstream | WNC Actions
Carry out process “quick wins” including: validation –guidance to staff on acceptable technical support documents consultation – reduce unnecessary consultation with internal and external stakeholders triage incoming applications for quick decisions | Achieving outcomes | Complete onboarding of DEF, WNC’s single software system for the Planning Service. Complete legacy process mapping exercise. Test temporary WNC processes and templates for a six-month period before a full review during 2024 to embed optimum unitary processes.

## Slide 12: Achieving Outcomes – Local Plan Engagement
PAS Recommendation | WNC Transformation workstream | WNC Actions
Develop a comprehensive approach, capitalising on the opportunities of a new unitary council, to involving and engaging involve internal and external stakeholders to work together to develop the new local plan. | Achieving Outcomes | Continuation of the production of the single Local Plan for West Northamptonshire. Update the Local Development Scheme (LDS) to ensure the milestones for the single Local Plan are refreshed and fit for purpose. Undertake a proactive consultation and engagement programme on the Local Plan.

## Slide 13: Achieving Outcomes – Local Plan Delivery
PAS Recommendation | WNC Transformation workstream | WNC Actions
Consider working with PAS to establish realistic project management arrangements for progressing the council’s new local plan. | Achieving Outcomes | Work with PAS to review the revised draft LDS and project programme before presenting to Planning Policy Committee. Work with PAS to review existing Local Plan evidence base, identify gaps and produce robust standard briefs for procurement.

## Slide 14: Achieving Outcomes – Governance S106/CIL
PAS Recommendation | WNC Transformation workstream | WNC Actions
Engage with PAS to benefit from their current support offer on improving the governance of developer contributions. | Achieving Outcomes | Undertake a DLUHC funded six-week review with PAS and Inner Circle Consulting to identify recommendations for a single process and governance framework for WNC. Ensure adequate resourcing corporately to deliver the project programme. Provide update to ELT and Members on the project programme and resource plan for corporate implementation. Work with PAS to deliver Member and Parish training on S106/CIL.

## Slide 15: Next steps
Feedback from today’s session – has it been useful?
Further session on S106 and CIL – 30th January 2024
Parish Questionnaire – January/ February 2024
Further session on the West Northamptonshire Local Plan – February/March 2024
Input into NCALC training programme 2024